## best_project
ID | Topic | Description | Material cost | Workers | Start date | End date
5 | Measuring campaign | Determination participants and loads | 0.0 | 1 | 09:00 Wednesday 12 September 2018 | 13:00 Wednesday 12 September 2018
6 | Measuring campaign | Drawing grid | 0.0 | 1 | 13:00 Wednesday 12 September 2018 | 13:00 Thursday 13 September 2018
7 | Measuring campaign | Measuring distances | 0.0 | 1 | 13:00 Thursday 13 September 2018 | 13:00 Saturday 15 September 2018
A3 | Electrical installation (Cluster A) | Digging C | 0.0 | 33 | 13:00 Saturday 15 September 2018 | 14:00 Saturday 15 September 2018
A1 | Electrical installation (Cluster A) | Digging A | 0.0 | 6 | 14:00 Saturday 15 September 2018 | 12:00 Monday 17 September 2018
A2 | Electrical installation (Cluster A) | Digging B | 0.0 | 1 | 10:00 Sunday 16 September 2018 | 10:00 Thursday 20 September 2018
A4 | Electrical installation (Cluster A) | Digging D | 0.0 | 4 | 14:00 Saturday 15 September 2018 | 14:00 Monday 17 September 2018
A5 | Electrical installation (Cluster A) | Digging E | 0.0 | 1 | 12:00 Sunday 16 September 2018 | 12:00 Thursday 20 September 2018
A6 | Electrical installation (Cluster A) | Digging F | 0.0 | 9 | 12:00 Thursday 20 September 2018 | 15:00 Thursday 20 September 2018
A7 | Electrical installation (Cluster A) | Digging G | 0.0 | 39 | 14:00 Saturday 15 September 2018 | 16:00 Saturday 15 September 2018
A8 | Electrical installation (Cluster A) | Cables A | 0.0 | 1 | 12:00 Monday 17 September 2018 | 12:00 Wednesday 19 September 2018
A9 | Electrical installation (Cluster A) | Cables B | 0.0 | 11 | 10:00 Thursday 20 September 2018 | 11:00 Thursday 20 September 2018
A10 | Electrical installation (Cluster A) | Cables C | 0.0 | 1 | 16:00 Sunday 16 September 2018 | 16:00 Monday 17 September 2018
A11 | Electrical installation (Cluster A) | Cables D | 0.0 | 1 | 10:00 Tuesday 18 September 2018 | 10:00 Thursday 20 September 2018
A12 | Electrical installation (Cluster A) | Cables E | 0.0 | 2 | 14:00 Thursday 20 September 2018 | 10:00 Friday 21 September 2018
A13 | Electrical installation (Cluster A) | Cables F | 0.0 | 1 | 10:00 Friday 21 September 2018 | 10:00 Saturday 22 September 2018
A14 | Electrical installation (Cluster A) | Cables G | 0.0 | 3 | 14:00 Tuesday 18 September 2018 | 10:00 Wednesday 19 September 2018
A15 | Electrical installation (Cluster A) | Installation overcurrent protection | 0.0 | 1 | 10:00 Saturday 22 September 2018 | 10:00 Monday 24 September 2018
A16 | Electrical installation (Cluster A) | Installation earth connection pin | 0.0 | 1 | 10:00 Monday 24 September 2018 | 10:00 Wednesday 26 September 2018
A17 | Electrical installation (Cluster A) | Filling A | 0.0 | 39 | 12:00 Wednesday 19 September 2018 | 14:00 Wednesday 19 September 2018
A18 | Electrical installation (Cluster A) | Filling B | 0.0 | 8 | 12:00 Friday 21 September 2018 | 14:00 Friday 21 September 2018
A19 | Electrical installation (Cluster A) | Filling C | 0.0 | 73 | 16:00 Monday 17 September 2018 | 09:00 Tuesday 18 September 2018
A20 | Electrical installation (Cluster A) | Filling D | 0.0 | 18 | 10:00 Thursday 20 September 2018 | 12:00 Thursday 20 September 2018
A21 | Electrical installation (Cluster A) | Filling E | 0.0 | 53 | 10:00 Friday 21 September 2018 | 11:00 Friday 21 September 2018
A22 | Electrical installation (Cluster A) | Filling F | 0.0 | 24 | 10:00 Saturday 22 September 2018 | 11:00 Saturday 22 September 2018
A23 | Electrical installation (Cluster A) | Filling G | 0.0 | 28 | 10:00 Wednesday 19 September 2018 | 11:00 Wednesday 19 September 2018
A24 | Electrical installation (Cluster A) | Installation lamps | 0.0 | 5 | 10:00 Wednesday 26 September 2018 | 10:00 Friday 28 September 2018
A25 | Electrical installation (Cluster A) | Construction technical space | 0.0 | 5 | 14:00 Thursday 27 September 2018 | 13:00 Friday 28 September 2018
A26 | Electrical installation (Cluster A) | Installation charge controllers/inverters/batteries | 0.0 | 1 | 12:00 Friday 28 September 2018 | 12:00 Wednesday 03 October 2018
A27 | Electrical installation (Cluster A) | Construction plateau for solar panels | 0.0 | 5 | 16:00 Tuesday 02 October 2018 | 16:00 Wednesday 03 October 2018
A28 | Electrical installation (Cluster A) | Installation solar panels | 0.0 | 1 | 16:00 Wednesday 03 October 2018 | 16:00 Thursday 11 October 2018
B5 | Electrical installation (Cluster B) | Digging L | 0.0 | 56 | 13:00 Saturday 15 September 2018 | 14:00 Saturday 15 September 2018
B1 | Electrical installation (Cluster B) | Digging H | 0.0 | 8 | 14:00 Wednesday 19 September 2018 | 10:00 Thursday 20 September 2018
B2 | Electrical installation (Cluster B) | Digging I | 0.0 | 7 | 10:00 Wednesday 19 September 2018 | 13:00 Wednesday 19 September 2018
B3 | Electrical installation (Cluster B) | Digging J | 0.0 | 48 | 14:00 Saturday 15 September 2018 | 15:00 Saturday 15 September 2018
B4 | Electrical installation (Cluster B) | Digging K | 0.0 | 6 | 14:00 Friday 21 September 2018 | 13:00 Saturday 22 September 2018
B6 | Electrical installation (Cluster B) | Digging M | 0.0 | 15 | 16:00 Friday 21 September 2018 | 11:00 Saturday 22 September 2018
B7 | Electrical installation (Cluster B) | Digging N | 0.0 | 35 | 11:00 Saturday 22 September 2018 | 12:00 Saturday 22 September 2018
B8 | Electrical installation (Cluster B) | Digging O | 0.0 | 36 | 15:00 Saturday 15 September 2018 | 16:00 Saturday 15 September 2018
B9 | Electrical installation (Cluster B) | Cables H | 0.0 | 1 | 16:00 Thursday 11 October 2018 | 16:00 Friday 12 October 2018
B10 | Electrical installation (Cluster B) | Cables I | 0.0 | 66 | 13:00 Wednesday 19 September 2018 | 14:00 Wednesday 19 September 2018
B11 | Electrical installation (Cluster B) | Cables J | 0.0 | 7 | 12:00 Friday 12 October 2018 | 14:00 Friday 12 October 2018
B12 | Electrical installation (Cluster B) | Cables K | 0.0 | 12 | 14:00 Friday 12 October 2018 | 16:00 Friday 12 October 2018
B13 | Electrical installation (Cluster B) | Cables L | 0.0 | 49 | 16:00 Saturday 15 September 2018 | 09:00 Sunday 16 September 2018
B14 | Electrical installation (Cluster B) | Cables M | 0.0 | 1 | 16:00 Friday 12 October 2018 | 16:00 Saturday 13 October 2018
B15 | Electrical installation (Cluster B) | Cables N | 0.0 | 42 | 12:00 Saturday 22 September 2018 | 13:00 Saturday 22 September 2018
B16 | Electrical installation (Cluster B) | Cables O | 0.0 | 1 | 12:00 Saturday 13 October 2018 | 12:00 Sunday 14 October 2018
B17 | Electrical installation (Cluster B) | Installation overcurrent protection | 0.0 | 1 | 12:00 Sunday 14 October 2018 | 12:00 Tuesday 16 October 2018
B18 | Electrical installation (Cluster B) | Installation earth connection pin | 0.0 | 1 | 12:00 Monday 15 October 2018 | 12:00 Wednesday 17 October 2018
B19 | Electrical installation (Cluster B) | Filling H | 0.0 | 17 | 16:00 Saturday 13 October 2018 | 10:00 Sunday 14 October 2018
B20 | Electrical installation (Cluster B) | Filling I | 0.0 | 15 | 10:00 Sunday 14 October 2018 | 12:00 Sunday 14 October 2018
B21 | Electrical installation (Cluster B) | Filling J | 0.0 | 33 | 12:00 Wednesday 17 October 2018 | 14:00 Wednesday 17 October 2018
B22 | Electrical installation (Cluster B) | Filling K | 0.0 | 82 | 16:00 Friday 12 October 2018 | 09:00 Saturday 13 October 2018
B23 | Electrical installation (Cluster B) | Filling L | 0.0 | 10 | 14:00 Wednesday 17 October 2018 | 16:00 Wednesday 17 October 2018
B24 | Electrical installation (Cluster B) | Filling M | 0.0 | 81 | 16:00 Saturday 13 October 2018 | 09:00 Sunday 14 October 2018
B25 | Electrical installation (Cluster B) | Filling N | 0.0 | 67 | 13:00 Saturday 22 September 2018 | 14:00 Saturday 22 September 2018
B26 | Electrical installation (Cluster B) | Filling O | 0.0 | 30 | 12:00 Sunday 14 October 2018 | 13:00 Sunday 14 October 2018
B27 | Electrical installation (Cluster B) | Installation lamps | 0.0 | 5 | 16:00 Wednesday 17 October 2018 | 16:00 Friday 19 October 2018
B28 | Electrical installation (Cluster B) | Construction technical space | 0.0 | 8 | 12:00 Friday 19 October 2018 | 16:00 Friday 19 October 2018
B29 | Electrical installation (Cluster B) | Installation charge controllers/inverters/batteries | 0.0 | 1 | 16:00 Friday 19 October 2018 | 16:00 Wednesday 24 October 2018
B30 | Electrical installation (Cluster B) | Construction plateau for solar panels | 0.0 | 1 | 12:00 Tuesday 23 October 2018 | 12:00 Sunday 28 October 2018
B31 | Electrical installation (Cluster B) | Installation solar panels | 0.0 | 2 | 12:00 Sunday 28 October 2018 | 12:00 Thursday 01 November 2018
19 | Cooling chamber | Drawing grid | 0.0 | 2 | 12:00 Wednesday 24 October 2018 | 16:00 Wednesday 24 October 2018
20 | Cooling chamber | Digging 3x3x2 | 0.0 | 41 | 16:00 Wednesday 24 October 2018 | 11:00 Thursday 25 October 2018
21 | Cooling chamber | Collecting materials | 0.0 | 1 | 16:00 Wednesday 24 October 2018 | 16:00 Thursday 25 October 2018
22 | Cooling chamber | Installation floor insulation + small floor plate | 0.0 | 4 | 16:00 Thursday 25 October 2018 | 16:00 Saturday 27 October 2018
23 | Cooling chamber | Masoning | 0.0 | 53 | 16:00 Saturday 27 October 2018 | 11:00 Sunday 28 October 2018
24 | Cooling chamber | Insulation | 0.0 | 2 | 12:00 Thursday 01 November 2018 | 16:00 Sunday 04 November 2018
25 | Cooling chamber | Assembling and installation roof | 0.0 | 2 | 12:00 Saturday 03 November 2018 | 12:00 Monday 05 November 2018
26 | Cooling chamber | Assembling and installation door | 0.0 | 3 | 12:00 Monday 05 November 2018 | 12:00 Tuesday 06 November 2018
27 | Cooling chamber | Installation heat pump | 0.0 | 1 | 12:00 Tuesday 06 November 2018 | 12:00 Saturday 10 November 2018
28 | Cooling chamber | Installation charge controllers/inverters/batteries | 0.0 | 1 | 16:00 Friday 09 November 2018 | 16:00 Wednesday 14 November 2018
29 | Cooling chamber | Installation solar panels | 0.0 | 1 | 16:00 Sunday 11 November 2018 | 16:00 Thursday 15 November 2018
30 | Cooling chamber | Installation racks | 0.0 | 30 | 12:00 Tuesday 06 November 2018 | 14:00 Tuesday 06 November 2018